## Sheet1
		rfid	tasks	hours estimate
			test new large antenna and reader	4
potentially done with hardware issues			order second large ant/reader	0.2
			Write and test software to record	5
			install in coop	5
			tag and record chickens	3
MVP to get data we want			write software to interpret data	3
			present data on web page for continuous usage	5
			change nesting boxes and install one in each	20
			query and display data

		water	tasks	hours estimate
ota updates, connect to wifi, receive commands			finish and test 120v wifi relay microcontroller	7
			prototype server software for relays	5
			test multiple wifi relays w server code	5
			run 120v to some valves	2
			Install 3 – 10 relays for testing	3
			field test / debug	10
MVP, no automation, just wireless control			install and test all relays for basic control	10
			write front end to set valves on schedule	10
			optimize for minimal pump run time
			maximize water use from schedule (water rows in 1 hour increments)

		weather stations	tasks	hours estimate
			research how to setup with wifi / hardware	5
			research how to receive data	5
			receive and store data	5
			functionality to query and display data	10